## Test Checklist
ASH1 Sensor Node Test Plan
Test # | Test Description | Status | Pass/Fail | Notes | Tester: | Test Date:
1A | Hardware Setup - Sensor Initialization |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
1B | Hardware Setup - LoRa Radio Initialization |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
2A | Sensor Reading - Temperature Accuracy |  | Pass | Within 2% of control group after settling time, our sensor is slower to respond | TR | 2025-12-02
2B | Sensor Reading - Humidity Accuracy |  | Pass | Within 4% of control group after settling time, our sensor is slower to respond | TR | 2025-12-02
2C | Battery Voltage Reading |  | Pass |  | TR | 2025-12-02
3A | LoRa TX - 15-Second Timing Test |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
3B | LoRa TX - Preamble "ASH1" Verification |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
3C | LoRa TX - Data Format Verification |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
3D | LoRa TX - Counter Increment Test |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
4A | LoRa RX - Receive from ASH2 |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
4B | LoRa RX - Preamble Filter
4C | LoRa RX - Reject Non-ASH2 Preambles
5A | Message Forwarding - Retransmit |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
5B | Message Forwarding - Preserve Original Data |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
6 | NVM - Counter Persistence Across Sleep |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
7 | LoRa Range |  | Pass | Satisfied with 200m line of sight | TR | 2025-12-03
8A | Power Efficiency - Current Draw Active
8B | Power Efficiency - Current Draw Sleep
9A | Integration Test - Full Cycle with ASH2 |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
9B | Integration Test - Full Cycle with ASH0 |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
9C | Integration Test - 3-Node System |  | Pass | Test was satisfied by ash0 test 5A | TR | 2025-12-01
Total Tests: | 21
Passed: | 17
Failed: | 0
Pass Rate: | 100%
Completion: | 80.95%

## Test Details
ASH1 Detailed Test Procedures
TEST 1: HARDWARE SETUP
Test 1A: Sensor Init | Power on device, check Serial output
Expected Results: | Serial: "SHT3x sensor initialized successfully."
If failed: Serial shows "SHT3x sensor failed to initialize." and error code
Test 1B: Radio Init | Verify LoRa radio initializes without HALT
Expected Results: | No RADIOLIB_OR_HALT error messages
TEST 2: SENSOR READINGS
Test 2A: Temperature | Compare sensor reading to known calibrated thermometer
Expected Results: | Within ±10% of reference
Test 2B: Humidity | Compare sensor reading to known hygrometer
Expected: | Within ±10% RH of reference
Test 2C: Battery Voltage | Use multimeter or osciliscope to verify vbat reading
Expected Results: | Within ±10% of measured voltage
TEST 3: LORA TRANSMISSION
Test 3A: 15s Timing | Monitor Serial - transmission should occur at millis() == 15000
Expected Results: | TX occurs 15 seconds after wake
Test 3B: Preamble | Verify transmission starts with "ASH1"
Expected Results: | Serial: TX [ASH1¦X¦Y¦Z¦W]
Test 3C: Data Format | Verify complete format with all fields
Expected Results: | Serial: TX [ASH1¦X¦Y¦Z¦W]
Test 3D: Counter | Monitor counter across multiple wake cycles
Expected Results: | Counter increments: 69, 70, 71, 72...
TEST 4: LORA RECEPTION
Test 4A: Receive ASH2 | Run ASH2, verify ASH1 receives its transmission
Expected Results: | Serial: RX [ASH2¦X¦Y¦Z¦W]
Test 4B: Preamble Filter | Verify only ASH2 messages are accepted
Expected Results: | pre_amb == "ASH2" check passes
Test 4C: Reject Others | Create transmission without and with different preamble near ASH1
Expected Results: | Serial: "intruder" for non-ASH2 preambles
TEST 5: MESSAGE FORWARDING
Test 5A: Retransmit | When ASH1 receives ASH2, data is parsed and forwarded
Expected Results: | Data from ash2 is parsed and included in the next TX
Test 5B: Preserve Data | Verify forwarded message is identical to received
Expected Results: | txForward = rxData (exact match)
TEST 6: NVM PERSISTENCE
Test 6: Counter NVM | Record counter, sleep, wake, verify persistence
Expected Results: | Counter continues from last value + 1
TEST 7: WIRELESS COMMUNICATIONS RANGE
Test 7A: LoRa Range | Verify device transmission with ASH0 receiving. Nodes within 30cm of each other
Move ASH1 away 10m at a time, leaving ASH0 at a fixed point, maintaining line of sight
Record distance, RSSI, SNR, and whether the packet was received.
Repeat up to 1km
Expected Results: | Rx over 1km without issue
TEST 8: POWER EFFICIENCY
Test 8A: Current Draw While Active | Connect ammeter between battery and BQ charge controller for one complete cycle
Expected Results: | More than sleep
Test 8B: Current Draw While Asleep | Connect ammeter between battery and BQ charge controller for one complete cycle (increase sleep time)
Expected Results: | Less than active
TEST 9: SYSTEM INTERGRATION
Test 9A: Full Cycle with ASH2
Expected Results: | Forwards message from ASH2
Test 9B:Full Cycle with ASH0
Expected Results: | Accepts transmissions from ASH1 and ASH2
Test 9C: 3-Node System
Expected Results: | Succesfull automatic triggering and data logging for ASH1 and ASH2

## Issues Log
ASH1 Issues and Problems
Issue # | Test # | Description | Severity | Status