## Test Checklist
ASH0 Solenoid Activation Test Plan
Test # | Test Description | Pass/Fail | Notes | Tester: | Test Date:
1 | Physical Button - Open Valve | Pass | Wix UI took >3 minutes to update | TR/EP | 2025-11-30
1 | Physical Button - Close Valve | Pass | Wix UI took >3 minutes to update | TR/EP | 2025-11-30
1 | Button Debouncing Test | Pass |  | TR/EP | 2025-11-30
2 | Web Command - Open Valve | Pass |  | TR | 2025-12-01
2 | Web Command - Close Valve | Pass |  | TR | 2025-12-01
3A | Fire Detection - Absolute Temperature | Pass | Wix UI took >3 minutes to update | TR | 2025-12-01
3A | Auto-Close After 2 Minutes | Pass | Wix UI took >3 minutes to update Auto-Close happens 20 minutes after the temperature drops below the threshold | TR | 2025-12-01
3B | Fire Detection - Absolute Humidity | Pass |  | TR, EP, MC | 2025-12-06
3B | Auto-Close After 2 Minutes | Pass |  | TR, EP, MC | 2025-12-06
3C | Fire Detection - Rate Of Change | Pass | Wix UI took >3 minutes to update | TR | 2025-12-01
3C | Auto-Close After 2 Minutes | Pass | Wix UI took >3 minutes to update | TR | 2025-12-01
3D | Backup Fire Check (LoRa Offline) | Pass |  | TR, EP, MC | 2025-12-06
4A | Button Override During Auto-Trigger | Pass |  | TR | 2025-12-01
4A | No retrigger for 1m | Pass |  | TR | 2025-12-01
4A | Retrigger after 1m | Pass |  | TR | 2025-12-01
4B | Web Override During Auto-Trigger | Pass |  | TR | 2025-12-01
4B | No retrigger for 1m | Pass |  | TR | 2025-12-01
4B | Retrigger after 1m | Pass |  | TR | 2025-12-01
4C | clearLocalData() Function Test | Pass |  | TR | 2025-12-01
5A | Rapid Source Switching Stress Test | Pass |  | TR | 2025-12-01
5B | Power Cycle During Auto-Trigger | Pass | See if this behaviour can be changed easily | TR | 2025-12-06
5C | WiFi Disconnect During Auto-Trigger | Pass |  | TR, EP, MC | 2025-12-06
Total Tests: | 22
Passed: | 22
Failed: | 0
Pass Rate: | 100%
Completion: | 100%

## Test Details
Detailed Test Procedures and Expected Results
TEST 1: PHYSICAL BUTTON
Setup: | System in normal operation, Wi-Fi connected, Receiving LoRa
Procedure: | Press physical button (GPIO 41)
Expected Results: | Once per button press
Serial: "Button - Valve state..."
LED toggles, solenoid toggles valve
MQTT publishes to field2 = "1" ¦¦ "0"
ThingSpeak field2 updates to 1 ¦¦ 0
Wix UI is updated to reflect the current valve state
TEST 2: MQTT COMMAND ACTIVATION
Setup: | System in normal operation, Wi-Fi connected, valve closed
Procedure: | Click activation button on website
Expected Results: | Serial: "Message [field2]..."
LED toggles, solenoid toggles valve
ThingSpeak field2 updates to 1 ¦¦ 0
Wix UI is updated to reflect the current valve state
TEST 3A: ABSOLUTE TEMPERATURE THRESHOLD
Setup: | System in normal operation, Wi-Fi connected ,LoRa receiving ASH1 transmissions
Trigger Condition: | Temperature ≥ 65°C
Procedure: | See Sensor Heating SOP
Expected Results: | Serial: "over max temperature"
LED turns ON, solenoid activates valve
Serial: "AUTO-TRIGGER..."
LED turns ON, solenoid activates
MQTT publishes to field2 = "1"
ThingSpeak field2 updates to 1
Wix UI is updated to reflect the current valve state
After 2 minutes:
Serial: "AUTO-TRIGGER TIMEOUT: Closing valve..."
LED turns OFF, solenoid deactivates valve
MQTT publishes to field2 = "0"
ThingSpeak field2 updates to 0
Wix UI is updated to reflect the current valve state
TEST 3B: ABSOLUTE HUMIDITY THRESHOLD
Setup: | System in normal operation, Wi-Fi connected ,LoRa receiving ASH1 transmissions
Trigger Condition: | Humidity ≤ 30%
Procedure: | See Sensor Heating SOP
Expected Results: | Serial: "under min humidity"
Auto-trigger sequence activates
Serial: "AUTO-TRIGGER..."
LED turns ON, solenoid activates valve
MQTT publishes to field2 = "1"
ThingSpeak field2 updates to 1
Wix UI is updated to reflect the current valve state
After 2 minutes:
Serial: "AUTO-TRIGGER TIMEOUT: Closing valve..."
LED turns OFF, solenoid deactivates valve
MQTT publishes to field2 = "0"
ThingSpeak field2 updates to 0
Wix UI is updated to reflect the current valve state
TEST 3C: RATE OF CHANGE (2 READINGS)
Setup: | System in normal operation, Wi-Fi connected ,LoRa receiving ASH1 transmissions
Array empty
Trigger Conditions: | Temp rise ≥ 3°C between last 2 readings AND Humidity drop ≥ 20% between last 2 readings
Procedure: | See Sensor Heating SOP
Expected Results: | Serial: "FIRE DETECTED: ...between last readings"
LED turns ON, solenoid activates valve
Serial: "AUTO-TRIGGER..."
LED turns ON, solenoid activates
MQTT publishes to field2 = "1"
ThingSpeak field2 updates to 1
Wix UI is updated to reflect the current valve state
After 2 minutes:
Serial: "AUTO-TRIGGER TIMEOUT: Closing valve..."
LED turns OFF, solenoid deactivates valve
MQTT publishes to field2 = "0"
ThingSpeak field2 updates to 0
Wix UI is updated to reflect the current valve state
TEST 3D: BACKUP FIRE CHECK
Setup: | System in normal operation, Wi-Fi connected, Sensor nodes offline (no LoRa reception)
Fire conditions exist in stored array
Trigger Conditions: | See rate of change tests
Procedure: | Either create triggering conditions using Sensor Heating SOP and disconnect ASH1 OR spoof array values
Expected Results: | After 10 seconds,
Fire detected from existing data
Auto-trigger activates without new LoRa
Serial: "AUTO-TRIGGER..."
LED turns ON, solenoid activates valve
MQTT publishes to field2 = "1"
ThingSpeak field2 updates to 1
Wix UI is updated to reflect the current valve state
After 2 minutes:
Serial: "AUTO-TRIGGER TIMEOUT: Closing valve..."
LED turns OFF, solenoid deactivates valve
MQTT publishes to field2 = "0"
ThingSpeak field2 updates to 0
Wix UI is updated to reflect the current valve state
TEST 4A: BUTTON OVERRIDE DURING AUTO-TRIGGER
Setup: | Auto-trigger active (valve open, LED ON)
Procedure: | Spoof array values to create auto-trigger on startup
Press physical button while timer running
Expected Results: | LED turns OFF, solenoid deactivates valve
TEST 4B: WEB OVERRIDE DURING AUTO-TRIGGER
Setup: | Auto-trigger active (valve open, LED ON)
Procedure: | Spoof array values to create trigger on startup
Click web button while timer running
Expected Results: | Serial: "Message [field2]..."
LED turns OFF, solenoid deactivates valve
TEST 4C: USER OVERRIDE DATA CLEARING
Setup: | Auto-trigger active (valve open, LED ON)
Procedure: | Spoof array values to create auto-trigger on startup
Assert either button while timer running
Use Sensor Heating SOP or spoof ASH1 data re-create triggering conditions
Repeat and use other user assertion method
Expected Results: | LED turns OFF, solenoid deactivates valve
Serial prints for array read 0
After 1 minute, arrays fill up and indicate fire conditions
LED turns ON, solenoid activates valve
Serial: "AUTO-TRIGGER..."
LED turns OFF, solenoid deactivates valve
TEST 5A: RAPID SOURCE SWITCHING
Setup: | System in normal operation, Wi-Fi connected, Receiving LoRa
Procedure: | In order, in quick succession
Press physical button (GPIO 41)
Click activation button on website
Press physical button (GPIO 41)
Click activation button on website
Repeat and switch order of user assertion method
Reapeat and add another assertion to end in activated state
Expected Results: | System handles without crashing
No GPIO conflicts
Final state is consistent with most recent assertion
TEST 5B: POWER CYCLING WHILE ACTIVE
Setup: | System in normal operation, Wi-Fi connected, Receiving LoRa
Procedure: | Activate solenoid valve to the open state using any assertion method. Auto-trigger, physical button, web button
Power cycle the control node
Expected Results: | Valve returns to closed until assertion
Assertion opens valve, turns on LED
TEST 5C: WI-FI DISCONNECT WHILE ACTIVE
Setup: | System in normal operation, Wi-Fi connected, Receiving LoRa
Procedure: | Spoof array values to create auto-trigger on startup
Turn off the Wi-Fi hotspot
Expected Results: | Reconection will block the auto shutoff, offsetting it by ~30s

## Issues Log
Issues and Problems Found During Testing
Issue # | Test # | Description | Severity | Status
1 | 1 | Button is clicking once on depression and again when released. Fixed, button was soldered to the phase pin | MAJOR | RESOLVED
2 | 2, 3A | Wix UI took >3 minutes to update | Moderate | NEEDS TESTING
3
4
5
6
7
8
9
10
11
12
13
14
15
16